## Event setup
The 2026 Gala Run-of-Show Template
Fill in the yellow cells. Every time on the Run of show tab is calculated from the doors time and the durations you set.
Setting | Your value | Notes
Event name | Northlake Health Foundation Spring Gala | Appears nowhere else — for your own reference.
Event date | 2026-05-09 | A real date — format it however you like.
Venue / room | The Grand Hall, Ottawa
Doors open | 18:00 | A real time value — the run of show counts forward from here.
Guests expected | 220
Auctioneer | Name of your auctioneer
AV lead | Name of your AV contact
Fund-a-need goal ($) | 50000 | Shown on the room display board during the appeal.
Silent sets | 3 | Sets close on a stagger so the checkout line never forms at once.
Minutes between set closes | 15 | See the Silent close stagger tab.
How to use this workbook
• Yellow cells with blue text are yours to edit. Everything else is calculated — leave it alone and it stays correct.
• Run of show: set a duration for each segment and the start times recalculate down the whole evening.
• Silent close stagger: set the first close time and the gap; each set's close is worked out for you.
• Fund-a-need script: the beats of the appeal, with the numbers your emcee should have in front of them.
• Print the Run of show tab for the AV booth and the auctioneer; they are the two people who need it on paper.

## Run of show
Run of show
Start time is calculated: each row begins when the row above it ends. Edit the duration, the segment, and the cues.
Start | Mins | Segment | Owner | Auctioneer / emcee cue | AV and music | Notes
| 35 | Doors, check-in opens | Registration | — | Walk-in playlist, house lights up | Card on file captured at check-in — no line at settlement.
| 30 | Reception, silent bidding opens | Committee chair | Two-minute welcome from the stage, then let the room work | Playlist continues, bid boards live | Guests scan the QR at their table.
| 15 | Guests seated, dinner service | Venue | Land the mission story before the first course clears | Mission video, lights to half | Keep it to three minutes.
| 15 | Silent set A closes | Auctioneer | Two-minute warning, then a countdown from ten | Countdown on the display board | Stagger the closes — see the stagger tab.
| 30 | Silent set B closes | Auctioneer | Same countdown, name the set | Countdown on the display board | Winners get a push notification as the set closes.
| 25 | Fund-a-need appeal | Auctioneer | Start high, come down the ladder, call every paddle by number | Thermometer on the display board, lights up on the room | See the Fund-a-need script tab.
| 10 | Silent set C closes | Auctioneer | Final close — tell the room this is the last one | Countdown on the display board | Held until after the appeal so the room stays in the appeal.
| 35 | Live lots | Auctioneer | Six lots, strongest lot third, close on the travel lot | Lot slides, spotlight on the podium | Clerk enters paddle bids for anyone bidding by hand.
| 15 | Thank-yous and close | Committee chair | Name the sponsors, name the total, send them home | House lights up, exit playlist
| 30 | Settlement, receipts send | Treasurer | — | — | Cards on file charge at close; receipts issue automatically.
Evening ends
Minutes are the input; start times are calculated. Change one duration and the rest of the evening moves with it.

## Silent close stagger
Silent close stagger
Sets close one after another so the settlement queue never forms all at once.
Set | Closes | Lots in set | Runner assigned | Notes
Set A |  | 14 | Table 1–6 runner | First close sets the tone — make the countdown loud.
Set B |  | 14 | Table 7–12 runner | Winners get a push notification the moment the set closes.
Set C |  | 12 | Floor lead | Reads off the Run of show tab — this set is held until the appeal is done.
Set A closes 80 minutes after doors by default. Change the gap between sets on the Event setup tab.

## Fund-a-need script
Fund-a-need script
The appeal is the single largest money moment of the night. Give the emcee the ladder and the numbers.
Beat | Say this | Ask level ($) | Paddles needed | Running total ($)
Set up the need | One beneficiary, named, in ninety seconds. No statistics yet.
Name the top ask | Who will start us at this level tonight? | 5000 | 2
Second level | Thank you. Now at this level — paddles up. | 2500 | 4
Third level | Keep them up, I am counting. | 1000 | 12
Fourth level | This is the level that fills the room. | 500 | 24
Floor level | Every paddle counts — last call at this level. | 250 | 64
Close the appeal | Read the total off the board. Thank the room by name where you can.
Appeal total if every level fills
Goal (Event setup)
Gap to goal
Ask levels and paddle counts are yours to set — the totals recalculate. A ladder that adds up to roughly 120% of goal leaves room for the levels that under-fill.